Welcoming Communities Vernon

Overview of Projects/Results – April 2014

### Background Information:

In the fall of 2012, the Province of BC launched a program called Welcoming Communities with the purpose of creating welcoming and inclusive communities for new immigrants throughout BC.  There is an understanding that immigrants provide important cultural diversity to local communities as well as skills, investment and an entrepreneurial spirit.  Canada has an aging demographic with a declining birth rate and will need to depend on immigration for social and economic growth in the upcoming decades.  It is important to support new immigrants and ensure they feel valued and part of local communities.

Social Planning Council for the North Okanagan (SPCNO) is the host agency for the Welcoming Communities Vernon Program.  In January of 2013, a community consultation was held with over 30 participants attending to provide feedback into the development of a Welcoming Communities Action Plan.  At that time, seven projects were identified and partnerships were developed to deliver the projects within the community.

Projects and Results:

| Projects | Lead Agency | Description | Final Results |
| --- | --- | --- | --- |
| Live Work Play Vernon | Chamber of Commerce | The Live Work Play project was designed to be a resource for employers of new immigrants, new immigrant entrepreneurs, and their families. It includes printed packages, and a web site with video. The website will be maintained by the Vernon Chamber. | The website can be viewed at www.welcomevernon.ca and printed materials are available through the Chamber of Commerce. |
| Diversity Training Feasibility Study | Nexus BC | This project was designed to assess the interest and commitment in the community for an on-going diversity training program. The project included a pilot training session attended by fifteen businesses. | The Diversity Training Feasibility Study has been completed. Please see attached report. |
| Public Audit | Social Planning Council | The public audit was designed to assess the welcoming aspects of a number of public sites from the point of view of the new immigrant. Several public buildings and services, and spaces were assessed by new immigrants using a set of criteria. From this assessment, several implementation activities were to be identified and developed within the timeframe of the program. | A Public Audit has been completed and a number of recommendations have been implemented. Please see attached report. |
| Multicultural Community Event Audit | Vernon Immigrant Services | The multicultural event audit was designed to assess current community events to determine how they could become more welcoming to new immigrants and/or to pilot a new event within the community. | Vernon Immigrant Services partnered with the DVA to introduce a multicultural theme into the Light Up event in November. |
| Public Art Project | Downtown Vernon Association | The public art project was designed as a participatory project to include new immigrants in the production of public art piece, while showcasing multicultural diversity and appreciation to the wider public. Immigrants worked on a mosaic tile that represented a fabric of the world under the guidance of a local artist. These have been installed in a public square with accompanying signage. A public launch of the art project took place in Civic Square in November 2013. | The Fabrics of the World art project is on display at Civic Square with interpretive signage. |
| School Inclusionary Teams | School District #22 | Inclusionary Teams were designed to create more welcoming spaces at schools and provided tools and resources to student teams to implement activities that would honour diversity and multiculturalism. | To date, 9 of the 17 schools in the district launched Inclusionary Teams and hosted school based activities. |
| Multi-Cultural Place Feasibility Study | Social Planning Council and Vernon Immigrant Services | The Multicultural Place Feasibility Study was developed to research the possibility of creating a space in the community to address identified gaps. These included: increasing Vernon and District Immigrant Services Society capacity to provide recreational space for New Immigrants; enhancing and accommodating multi-cultural organizations’ need for meeting and event space; as well as to help raise the profile of multiculturalism in the community. | The Multi-Cultural Place Feasibility Study has been completed. Please see attached report. |

### Next Steps:

As of April 1, 2014, the federal government is funding the second phase of the project.  A two year contract has been awarded to the Social Planning Council to administer and oversee the development of a Strategy to Attract and Retain Immigrants to Vernon.  Consultants have been hired to lead the project and the first Steering Committee will be held in June 2014.